## Sheet1
Header | Data Type/Format | Formula | SO Comments | KF Comments
C-Suite Dashboard
Total Development Cost (TDC)
Baseline Approved Budget vs Forecasted Estimate at Completion (EAC)
Milestone Volatility
Variance Days
Contingency Burn Rate vs. Physical Progress
% of Project Contingency Spent vs % of Physical Construction Complete
Unapproved Claims & Change Order Exposure
Total Dollar Value of Pending/Unapproved PCOs & Average Days PCO sit in review
Safety and Health Compliance
TRIR
Pull Below Items into a TOP 5 Risk Register for RED/YELLOW
Leadership Reporting
Project_ID | Text
Project_Name | Text
Date_As_Of_Date | Date
Revenue | Currency
Planned Margin | Currency
Forecast/Actual Margin | Currency
Safety Performance | Traffic light
Cost Performance Index | Traffic light
Schedule Performance Index | Traffic light
Progress (Planned vs Actual) | Traffic light
Cash flow | Traffic light
Health, Safety & Enviornment (HSE) |  |  | Develop traffic light that will be linked to the leadership reporting (green, orange, red)
Total_Hours | Number
Safe_Days_Since_Incident | Number
First_Aid_Incidents | Number
Recordable_Incidents_TRIR | Number
Lost_Time_Incidents_LTIR | Number
Safety_Observations_Resolved | Percentage
Quality
Open_RFI_Count | Number
Avg_RFI_Response_Time_Days | Number
Open_Punchlist_Items | Number
Rework_Cost_Incurred | Currency
Financials |  |  | CPI, cashflow positive, margin trend
Original Project Cost | Currency
Actual_Cost_To_Date | Currency
Earned_Value_To_Date | Currency
Estimate_At_Completion_EAC | Currency
Variance_At_Completion_VAC | Currency
Pending_Change_Order_Count | Number
Pending_Change_Order_Value | Currency
Original Contingency | Currency
Total_Contingency_Remaining | Currency
Contingency burned rate | % |  | To be aligned with contingency allocation & progress
Billed_To_Date | Currency
Cash_Recieved_To_Date | Currency |  | Major cashflow trend (positive/negative)
Days for receivable | #
Net Cash Position | Number | Cash_Received_To_Date - Actual_Cost_To_Date
Cost Performance Index (CPI) | Number | Earned_Value_To_Date / Actual_Cost_To_Date
Cost Variance at Completion (VAC) | Number | Current_Budget - Estimate_At_Completion_EAC
Schedule, Progress, & Milestone
Customer's need date
Baseline_Finish_Date | Date
Forecast_Finish_Date | Date
Schedule Performance Index (SPI) | Number | Earned_Value_To_Date / Budget_To_Date
Milestone Variance (Days) | Number | Forecast_Finish_Date - Baseline_Finish_Date
Milestone_Name | Text
Schedule_Variance_Days | Number | Forecast_Date - Baseline_Date
Percent_Complete_Physical | Percentage | Actual physical progress
Critical_Path_Impact | Y/N
Other Construction Trackers
GC_Buyout_Status_Percent | Percentage
Owner_Contingency_vs_GC_Contingency | Currency
Stored_Materials_Value_Offisite | Currency
PCO_Age_Days | Number
Weather_Days_Claimed_To_Date | Number
RFI_Critical_Path_Impact_Count | Number
AHJ_Permit_Status | Text
Cx_PreRequisites_Percent | Percentage
Lien_Waiver_Compliance_Status | Y/N
AHJ_Inspection_Pass_Rate | Percentage
Actual_vs_Planned_Daily_Headcount | Percentage
Retainage_Withheld_To_Date | Currency
Net_Payable_This_Month | Currency
Cost and Schedule Category
Cost/Schedule_Category | Dropdown |  | Land, site development, power & utilitites, LLE & Material procurement, GC, fitout, O&M
Vendor_Name | Text
Original_Commitment | Currency/date
Approved_Change_Orders | Currency/days
Current_Commitment | Currency/date
Pending_Change_Orders | Currency/days
Invoiced_To_Date | Currency
Paid_To_Date | Currency
Accounts_Payable_Aging | Currency
Estimate_At_Completion_EAC | Currency